## Sheet1
Module | Task | Team Member(s) | 2018-02-26 | 2018-03-01 | 2018-03-02 | 2018-03-03 | 2018-03-04 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2018-03-11 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-17 | 2018-03-18 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-04-23 | 2018-03-24 | .
Programming Industrial Robots | Set Up Git Hub Repository and Task Allocation | All
| Report Set Up and Introduction | Robert and Faisal
| Initial Research and Study Of Mitsubishi Arm | Jack
| Initial Testing And Programming Outline | Spencer And Faisal
| Virtual Simulation And Testing | Faisal
| Program Build And Test | Spencer
| Test And Finalisation | Jack and Robert
| Finish Report | All
Manipulator Design Project | Set Up Git Hub Repository and Task Allocation | All
| Report Set Up and Introduction | Spencer and Robert
| Initial Research and Study Of Freeform movement/inverse kinematics/actuators/3D print materials/software/sensors | All
| Calculation of Arm Movement Part A (Inverse Kinematics) Redundant Section | Faisal and Spencer
| Calculation Of Arm Part B (Forward Kinematics of End Effector) | Jack and Robert
| Materials And Loads Calculations | Faisal and Spencer
| Initial thumbnail sketches and Design Finalisation | All
| Build And Test | Jack and Spencer
| Simulation Build And Test | Faisal and Robert
| Design Improvements/ Error Correction | All
| Finalisation and Demonstration | All
| Report Finalisation | All
Team Members:
Spencer Perdomo-Davies,
Faisal Fazal-Ur-Rehman,
Robert Grainger,
Jack Gell
S